## Sheet1
Name | Task | Dask Discription | Date Assigned | Date Due | Status | Priority
Anrich Van Zyl | Create Basic UI | Create a main login form Creat main ppage with fields to display and input values Create other pages that might we will need later on (abou, contact us etc) | 2020-05-15 | 2020-05-20 | Incomplete | Mission Critical
Hermann Roets | Start On Business Objects | Start with the creation of the business objects | 2020-05-20 | 2020-05-25 | Incomplete | None | Anrich Van Zyl
Tian Hannekom | Create ERD | Create ERD based on business needs | 2020-03-15 | 2020-05-18 | Complete | None | Hermann Roets
Tian Hannekom | Create Database | Create the database tables | 2020-05-18 | 2020-05-20 | Incomplete | Mission Critical
Jochemus Taljaard | Create stored procedures | Basic Insert,Update,Delect,Select | 2020-05-19 | 2020-05-23 | Incomplete | High | Phill McCarter
Tian Hannekom | Create stored procedures | More Advanced Procudres | 2020-05-20 | 2020-05-25 | Incomplete | None | Tian Hannekom
Phillip McCarter | Create Datahandler | Add Basic Methodes to access and store data usi8ng stored Procudres |  |  | Incomplete | High
[5 empty] | Incomplete | None
[5 empty] | Incomplete | None
[5 empty] | Incomplete | None
[5 empty] | Incomplete | None
[5 empty] | Incomplete | None